## Sheet1
IMPERATIVE | OBJECTIVES | STRATEGIES | PERFORMANCE METRICS | DESIRED OUTCOMES | LEAD | PARTICIPANTS | TIMELINE | BUDGET | POTENTIAL FUNDING SOURCES
OUTREACH AND EDUCATION IMPERATIVE | Promote tools and information for water conservation. Foster a culture of water conservation. Build capacity of constituents to advocate for state and federal resources and funding. Support training and professional development to ensure the availability of skilled water technicians. | 1. Develop and implement a public awareness program aimed at changing behaviors of all water users. Note: Individual components of program listed below. | Annual increase in engagement with residents, visitors, and industry about water resources. Residents, visitors, and industries are aware of and are practicing a culture of water conservation. Public and private water suppliers are participating in water outreach to communities. There is uniform region-wide messaging about water use and conservation. | Residents and industries in, and visitors to, the Mid-Coast region are aware and proud of, and practicing a culture of water conservation. Public and private water suppliers are participating in water management and conservation planning and outreach to communities. Uniform region-wide messaging about water use and conservation. | Education (all levels), interpretive facilities (Oregon Coast Aquarium, HMSC), regional water providers (private and public), OWRD, Oregon State University Extension Services | Water use industries, tourism industry, water rights holders | PHASES I-II |  | Oregon Health Authority Drinking Water Source Protection Grants & Loans (Eligible projects include but are not limited to outreach/education, monitoring efforts (outside of what is required by the state), restoration design and implementation, groundwater risk assessments. Publicly and privately-owned community and nonprofit non-community water systems are eligible to apply for DWSPF funding.) Oregon Community Foundation's Oregon Natural Resources Education Fund invites proposals from high school organizations providing natural resources education. Funding is available for natural resource related tools, equipment, technology and other educational resources. Autzen Foundation: Grants are awarded to smaller non-profit organizations; most often to groups with social service, arts and culture, educational, environmental and/or youth-centered missions.
|  | a. Promote water conservation at local events, on the MCWPP website and the websites of regional partners and entities, in news articles, in water bills, via social media, and through outreach materials to businesses, particularly in the hospitality industry. |  |  | Education (all levels), interpretive facilities (OR Coast Aquarium, Hatfield Marine Science Center), water providers, ORWRD, Oregon State University Extension Services | Water use industries, tourism industry, water rights holders | PHASES I-II | 50000
|  | b. Develop drought declaration and audience-specific (e.g., self-supplied industrial water users) water conservation and curtailment messages. |  | Messaging associated with drought and water curtailment, which is consistent as practicable across the Mid-Coast, is developed and distributed. | Mid-Coast water providers (e.g., Mid-Coast Water Conservation Consortium), Lincoln County Board of Commissioners |  | PHASE I | 40000
|  | c. Coordinate watershed and water system tours to increase awareness and understanding of regional and local water issues. |  | Increased understanding of regional and local water issues. | Mid-Coast Water Planning Partnership |  | PHASE I-III | 100000 | Grants are awarded to smaller non-profit organizations; most often to groups with social service, arts and culture, educational, environmental and/or youth-centered missions. Could potentially be encompassed in a Meyer Memorial Trust Grant.
|  | d. Connect private landowners with resources and information about best management practices to improve water quality and quantity. |  | Landowners are connected with resources and information about BMPs to improve water quality and quantity. | Local stewardship foresters, local SWCD staff, and USDA NRCS, OSU Extension, ODF |  | PHASE I | 50000
|  | e. Develop curriculum for students about their water sources, water management, and water conservation. |  | Students are learning about their water supply and the importance of water conservation, and they share that information with family members. | MCWCC, ducation (all levels), interpretive facilities (OR Coast Aquarium, Hatfield Marine Science Center), water providers, ORWRD | Water use industries, tourism industry, water rights holders | PHASE II | 75000
|  | f. Develop a regional initiative/training to improve coordination and provide education to water providers on infrastructure financing and funding. |  | Water providers receive information on infrastructure financing and funding. | Water providers, MCWCC, Fund Managers |  | PHASE I | 50000 | Meyer Memorial Trust, Oregon Community Credit Union (OCCU) Foundation
|  | g. Support an internship program that provides hands-on training for water technicians. |  | Each water provider has an updated water management and conservation plan they are implementing. | Water providers and water users, all municipalities |  | PHASE II | 250000 | Autzen Foundation: Grants are awarded to smaller non-profit organizations; most often to groups with social service, arts and culture, educational, environmental and/or youth-centered missions. Maybelle Clark Macdonald Fund supports projects in the areas of education, human services & public benefit. Oregon Community Credit Union (OCCU) Foundation.
|  | h. Advocate for the implementation of voluntary, incentive-based actions in the Mid-Coast Agricultural Water Quality Management Area Plan. |  | Voluntary, incentive-based actions effectively help to deliver on the goals on the Mid-Coast Agricultural Water Quality Management Area Plan. | Agricultural water users |  | PHASES I-III | 50000
|  | i. Inform self-supplied water users with water quality information from source waters and water protection measures, including proper well construction and maintenance. Provide outreach/education on septic system management to protection groundwater and surface water. |  | Self-supplied water users can access available WQ information concerning source water, implement measures to reduce impacts on source water quality, conduct regular inspection, maintenance and repairs (as needed) of septic systems, and understand how to access and use available WQ data. | OHA, OSU Extension, County, DEQ, water providers |  | PHASES I-III | 50000
|  | j. Partner with agencies and Oregon State University Extension to deliver information on safe pesticide application practices and vegetation management practices that reduce or eliminate pesticide use. Provide outreach on water quality impacts of pesticides and fertilizers associated with lawn management near streams and ponds. Share methods that reduce impacts and identify alternatives. |  | Pesticides are applied minimally and safely throughout the region. Options are developed that reduce impacts and provide alternatives to pesticides. | ODA, OHA |  | PHASES I-III | 50000
|  | k. Conduct education in source water areas (to those that may not be customers of the water provider) about drinking water sources, risks, choices, and strategies. |  | The public is aware of and supports source water protection measures. | Education (all levels), interpretive facilities (Oregon Coast Aquarium, HMSC), regional water providers (private and public), OWRD, Oregon State University Extension Services |  | PHASES I-III | 50000
PLANNING AND COLLABORATION IMPERATIVE | Cultivate active coordination and collaboration among all regional water providers to improve access to resources and funding that enhance system resilience and reliable source water quantity and quality. Expand water conservation planning programs and initiatives. | 2. Support the creation of a feasible 50-year county-wide water supply plan. | Increase in water plans that are developed and updated, and consistent with the MCWPP Water Action Plan. | Conduct an updated analysis of supply and demand (use OSU Study) coupled with an alternatives analysis of potential strategies to reduce demand and/or increase supply (conservation, pricing, storage, reuse, new sources, etc.). | Lincoln County, Regional Solutions, Lincoln County Water Systems Alliance (LCWSA) | All Lincoln County water suppliers, regional stakeholders, OWRD and other state agencies) | PHASES I-III | 200000
|  | 3. Develop and update water management and conservation plans for the Mid-Coast regional municipal and self-supplied direct water systems. |  | Each water provider on the Mid-Coast has a recently updated water management and conservation plan appropriate in scale for the size of their customer accounts and demand. | Water providers and water users, all municipalities |  | PHASE II | 100000
|  | 4. Coordinate water curtailment plans for water providers. |  | Water providers coordinate water curtailment plans and messaging to the extent practicable, particularly those sharing water systems and sources. | Entities with shared water systems/sources, MCWCC | OWRD | PHASES I-II | 15000
|  | 5. Develop Drinking Water Protection Plans to ensure that strategies and implementation plans are in place to minimize threats to water supply sources. |  | Drinking Water Protection Plans are developed. | Water providers |  |  | 100000
|  | 6. Create a Source Water Protection Plan, or multiple source-specific plans, to reduce, or minimize contaminants from entering source waters. Advocate for funding to support the development and implementation of these plans. |  | A source water protection plan, or multiple plans, include actions that minimize contaminants entering source waters. | Lincoln County, water districts, city, DEQ, OHA, OHA |  | PHASE II | 2000000
|  | 7. Encourage municipalities to update/complete stormwater management control plans to incorporate Green Infrastructure/Low-Impact Development practices, using statewide LID technical design guide, and update codes and ordinances that are barriers to implementing these practices. Assist smaller communities, that are not currently required, in developing similar stormwater management plans and technical design guides. |  | Municipal stormwater management control plans are updated and completed. | Municipalities |  | PHASE III | 100000
|  | 8. Ensure Emergency Response Plans (required for public water systems) address water system needs and specific vulnerabilities, and are interconnected to create a regional network during emergency situations. |  | Public water system suppliers develop comprehensive plans that address the full suite of emergency measures needed locally and regionally. | OHA/County, DEQ water providers |  | PHASE II | 50000
|  | 9. Collaborate with emergency operations planners to identify highest priority water needs and develop alternative systems and plans. Identify opportunities and access for shared water available for addressing emergency interconnections. | Annual increases in collaboration across Mid-Coast water providers. | Water vulnerabilities are clearly articulated in updates to the Natural Hazard Mitigation Plan. | Water providers, MCWCC |  | PHASE I | 125000
|  | 10. Support the development of organizational procedures for the Mid-Coast Water Conservation Consortium (MCWCC) and the Lincoln County Water Systems Alliance (LCWSA) that will facilitate the prioritization and funding of projects throughout the region. |  | The Mid-Coast Water Conservation Consortium (MCWCC) and the Lincoln County Water Systems Alliance (LCWSA) are structured to prioritize and fund water projects in the region. Explore organizational options for Mid-Coast Water Conservation Consortium that would enable entity to prioritize and fund projects throughout the region on behalf of members. | MCWCC, LCWSA | Independent, governmental, and industrial water suppliers and users | PHASE II | 50000 | Meyer Memorial Trust Capacity Building Grant
|  | 11. Strengthen/support the MCWCC (water suppliers that address water conservation issues) to enhance water conservation, increase resiliency during shortages and emergencies, and pool resources of multiple water providers. Support enhanced coordination with state and federal entities outside of the Mid-Coast. |  | Water suppliers have a strengthened ability to address water conservation issues, increase resiliency, and pool resources. | MCWCC, LCWSA | Water providers | PHASE I | 50000
|  | 12. Develop tiered communication trees to address: a) typical support needs (materials, expertise, spare hands); b) response to localized emergencies affecting one or multiple Public Water Systems (but not a majority); and c) Cascadia Subduction Zone quake, volcanic eruption, regional wildfire. Provide communication alternatives for inoperable phone/internet (HAM resources; meeting locations and days/times). |  | Ensure a mutual aid network exists on the coast to communicate and respond effectively during emergencies. | Lincoln County, water providers, MCWCC |  | PHASE II | 50000
|  | 13. Support and advocate for the compilation of a hierarchy of necessary spatial analyses and modeling to determine which conservation strategies, and locations on the landscape, will result in the greatest environmental returns on investment (ROI) (e.g., ecological function) and achieve the highest priorities in existing species recovery plans (e.g., improving winter and summer rearing habitats). Advocate for implementation of strategies in federal Coho recovery plan and Oregon coast Coho Conservation Plan (OWEB FIP Framework). |  | Spatial analyses are conducted/compiled to identify strategies, and locations on the landscape, to achieve the greatest environmental returns on investment (ROI) (e.g., ecological function) and support existing recovery plans. Actions support existing recovery plans. | MCWCC, OWEB, DEQ, USFS, LCSW, OWRD, Lincoln County | EPA (Bob McKane/VELMA modeling) | PHASE II | 250000
|  | 14. Support and advocate for planning and development that minimizes impacts to floodplains and riparian areas, and uses Green Infrastructure Methods and Low Impact Development practices. |  | Natural storage (e.g., beaver protection) is supported, and open zoning regulations that promote marshland migration are encouraged. Planning and development minimizes impacts to floodplains and riparian areas through the implementation of GIM and LID practices. | County planners, DLCD, municipal planning departments | US Forest Service, DEQ, ODFW, ODF | PHASES I-II | 50000 | Bureau of Reclamation Cooperative Watershed Management Grant (Phase I)
|  | 15. Evaluate the information available (peer-reviewed science) on how stream flows are impacted by land use practices. |  | Peer-reviewed science is reviewed to evaluate how stream flows are affected by land use practices. | Oregon State University Extension |  |  | 50000
MONITORING AND DATA SHARING IMPERATIVE | Improve the effectiveness of water quality and quantity monitoring programs throughout the region. Assess the levels and presence/absence of contaminants in Mid-Coast waters and describe negative effects to human health. Sample throughout the Mid-Coast to accurately identify the quantity and type of toxics entering source waters to assess potential risks to both drinking water quality and aquatic life. Provide self-supplied water users with adequate and timely data to determine regional, local, or site-specific water quality contamination issues that may pose a health risk. | 16. Implement more efficient advanced metering infrastructure to enable faster identification of leaks and shortages, and support best practices for water providers to meet industry standards for documenting water loss. | Increase in the quantity, methods, accuracy, and sharing of water monitoring and data in the Mid-Coast region. Access to water information data is widely available and understandable to the public. | Real-time information on water use and water loss is documented to better manage water and engage everyone in water conservation. 75% of connections in the Mid-Coast region have meters/associated infrastructure (apps, online platform) within 5 years. Water providers are documenting unaccountable water loss. By 2030, all water providers in the Mid-Coast region demonstrate systems have 10% or less unaccountable water loss. | Water providers, MCWCC | OWRD | PHASES I-III | 3000000
|  | 17. Recommend installation and use of flow meters to gain a more accurate estimate of water use in the region. |  | Installation of flow meters on withdrawals is prioritized using an established set of criteria. | Local SWCD (with resources), OWRD |  |  | 100000
|  | 18. Fully fund, install, and monitor real-time stream gauging stations throughout region in priority locations and times of year when they are needed most to accurately assess source water and enable innovative demand-reduction actions during periods of critical ecological need. |  | Identify sites for highest priority gages. Funding and staff secured to maintain monitoring network. An updated basin study that addresses water uncertainties in the Mid-Coast region (improved granularity of measurements). Exploration of newer AI technologies is supported by the partnership. Real-time river monitoring/gauging is conducted in priority locations. | USGS, ODFW, OWRD, private landowners, OWEB, watershed councils, organizations, water providers |  | PHASE I | 200000
|  | 19. Develop and implement a long-term water quality monitoring program throughout the region (e.g., source water, streams, estuaries) to improve understanding of baseline conditions and event-caused conditions (i.e., storm, low-flow) for nutrients, bacteria, temperature, dissolved oxygen, pH, turbidity and other specific contaminants identified by DEQ, including those that contribute to harmful algal blooms (HAB)s. Collect water samples to identify pollutant sources (location, source, practices influencing input, transport and fate of pollutants). Advocate for additional sampling in headwaters (where herbicides and pesticides are applied and at municipality intakes). |  | Real time data sharing occurs among municipalities, and there is frequent testing of source waters. Samples are taken in headwaters and City intakes at the frequency needed to track source water quality status. Outreach and incentive programs reach landowners who then modify practices and implement best management practices. | DEQ, OHA, US FS, OWRD, Counties, cities, MCWC, LSWCD, state and private forestry sector (ODF), Agricultural sector (ODA lead) |  | PHASES I-II | 1000000 | Oregon Health Authority Drinking Water Source Protection Grants & Loans (Eligible projects include but are not limited to outreach/education, monitoring efforts (outside of what is required by the state), restoration design and implementation, groundwater risk assessments. Publicly and privately-owned community and nonprofit non-community water systems are eligible to apply for DWSPF funding.)
|  | 20. Conduct comprehensive and ongoing water testing, and use results to guide best management practice implementation, restoration, etc. to address water quality impairments. |  | Ongoing and comprehensive water testing is conducted, and the results are used to guide management efforts. Education and outreach and testing is conducted on private wells on a regular basis. | DEQ, OHA, USFS, Counties |  | PHASES I-III | 100000
|  | 21. Develop a coordinated network of people conducting stream flow monitoring and water quality monitoring to share resources and data. Explore cost-effective ways to incorporate volunteers in data collection to complement gauging network. |  | A robust coordinated network of volunteers are conducting stream flow and water quality monitoring and sharing that information via a Mid-Coast network. | Lincoln County | MCWCC, SWCD, OWRD, DEQ, OWEB, Salmon-Drift Creek WC, US Forest Service | PHASE II | 100000
|  | 22. Support the aggregation and update of current self-supplied water system databases, including system description, system status, and system needs. Determine what exists from current databases. Track wells going dry via self-reporting. NOTE: OE database group will be discussing. |  | There is comprehensive regional knowledge of self-supplied water system information in the Mid-Coast Region. | Lincoln County | Private well drillers, private septic companies, OWRD well log database | PHASE I | 125000 | Oregon Health Authority Domestic Well Safety Program (DWSP)
|  | 23. Develop a water monitoring database for data entry and access by multiple entities. |  | A water monitoring tool that consolidates water data for the public and water managers to access and use. The Mid-Coast serves as a pilot to demonstrate water quality and quantity database sharing. | Stream Team | Local, State, and Federal agencies, and private citizens | PHASE I | 100000
WATER CONSERVATION AND REUSE IMPERATIVE | Effectively use limited water supplies, especially during times of water shortage. Reduce water use. | 24. Use recycled and gray water to irrigate landscapes. | Increase in the amount of recycled and gray water used by water consumers in the Mid-Coast region. | An analysis of regulatory issues and pilot/model programs is conducted to determine realistic and safe options for the use of recycled water. | ORDEQ, OHA, Water providers | Homeowners and businesses | PHASE II | 150000
|  | 25. Conduct Water Reuse ¦ Promoting Sustainable Water Sources and Clean Water Services for developed methods of reusing treated sewage plant water and water at water at water treatment plants (e.g., backwash) for potable and industrial uses. |  | Everyone learns from others that have successfully implemented innovative strategies to meet water needs. Lower levels of solids are achieved in pre-treatment programs (e.g., sidestream; potential energy sources) to maintain infrastructure longer. Reuse of backwash water is encouraged. | MCWCC, Water providers | OR DEQ, OHA, OWRD, Clean Water Services (Hillsboro, Oregon - cleanwaterservices.org), WateReuse (https://watereuse.org) | PHASE I | 100000
|  | 26. Consider water pricing strategies and other strategies to stimulate water conservation and raise revenue. Explore water savings opportunities at commercial facilities. | Increase in the availability and use of water conservation incentives among all stakeholders. A culture of water conservation is furthered through developers as well as municipal water providers (planning and public works departments/committees) embracing and incorporating water saving technologies and design strategies. | A regional alternatives analysis is conducted that compared different alternatives for meeting current and future water needs for individual water providers and the region as a whole. A comprehensive rate study is conducted that considers tiered rate methodology. | Water providers | OWRD, Oregon State University | PHASE I | 150000
|  | 27. Work with the NRCS to develop a Conservation Implementation Strategy to cost-share with agricultural irrigators on irrigation system improvements, pursuing incentives and support for irrigators that want to increase efficiencies to minimize evaporation losses. |  | Agricultural irrigators that are able to access incentives and other cost-share opportunities to conserve water and enhance efficiencies. By 2023, an RCPP (RCPP – Regional Conservation Partnership Program) is established in the region. Incorporation of existing global technologies to enhance irrigation efficiencies. | Natural Resources Conservation Service, McKenzie River Trust | Agricultural irrigators (engage in development and implementation of strategy) | PHASE II | 1500000
|  | 28. Establish a revolving loan program for infrastructure improvements for septic systems. |  | Loans are available on a consistent basis. | Lincoln County |  | PHASE II | 200000
|  | 29. Develop voluntary incentives for water conservation. |  | Develop and implement incentives (rebates on equipment, tax breaks, monthly water bills, free water-saving items, recognition (awards or labels) of conservation for businesses) to stimulate voluntary water conservation. | Water providers, MCWCC, Lincoln County | OWRD, water users | PHASES II-III | 100000
WATER INFRASTRUCTURE IMPERATIVE | Create more resilient infrastructure. Replace aging infrastructure. Create redundancy, water system interconnections, and alternative sources of water to ensure access to safe drinking water in case of emergencies. | 37. Improve efficiency of irrigation systems and replace aging systems. | Annual increases in the percent of aging and inefficient water infrastructure that is replaced and enhanced. | Aging systems are replaced, and the efficiency of existing systems is improved. | NRCS CIS and RCPP |  | PHASE II | 500000 | OWRD Water Projects Grants and Loans; Clean Water State Revolving Fund (CWSRF) will fund irrigation modernization projects for water efficiency if it benefits water quality. USDA SEARCH - Special Evaluation Assistance for Rural Communities and Households Program. OHA's Safe Drinking Water Revolving Loan Fund (SDWRLF).
|  | 38. Support upgrading and maintaining water metering system infrastructure, where possible. Note: Automated read systems (not SMART) can be installed at reduced cost. |  | Install smart water grid systems in Mid-Coast communities. Achieve water balance in community systems (Stream to Tap). | Water providers, MCWCC |  | PHASE II | 1500000 | OHA's Safe Drinking Water Revolving Loan Fund (SDWRLF).
|  | 39. Use the latest technologies (e.g., In system monitoring and controls, pumping efficiency, automating and controlling potential zone isolations) available when retrofitting, or replacing, water infrastructure. |  | Isolations are implemented in emergencies. | Water providers |  | PHASE III | 200000
|  | 40. Use green/natural infrastructure to create resilience that can support insufficient water infrastructure to help prevent water shortages. |  | Natural infrastructure enhances resilience and helps to prevent water shortages. |  |  | PHASE I | 200000
|  | 41. Address distribution system failures by installing earthquake valves in water tanks to retain water even if distribution system fails. |  | Expanded water system monitoring and controls are in place. | Water providers |  | PHASE II | 1000000
|  | 42. Work with the NRCS to develop a Conservation Implementation Strategy to cost-share with agricultural irrigators on irrigation system improvements, pursuing incentives and support for irrigators that want to increase efficiencies to minimize evaporation losses. |  | Achieve enhanced water resiliency infrastructure in the Mid-Coast region. |  |  | PHASE III | 250000
|  | 43. Support the expansion of the state-supported revolving fund (including developing a new fund for self-suppliers) to accelerate water infrastructure improvements. Improve access to funding by enhancing coordination and collaboration with communities). |  | Funding options for individual providers and the region are well understood, and a strategy exists to upgrade and maintain critical infrastructure. Mid-Coast water providers have capital improvement plans. | Business Oregon (1-stop program) (Infrastructure Finance Authority) | MCWCC (educational role for municipalities), OWRD and other funding agencies | PHASE III | 4000000 | USDA Rural Development Circuit Rider Program. OWRD has a $14-20M biennial revolving fund.
|  | 44. Identify funding programs to support infrastructure enhancements that advance sustainable and secure water solutions for the region. Study how other cities and counties have funded their infrastructure improvements through time. |  | Natural storage (e.g., beavers) projects are implemented. Invasive species are eradicated, or controlled, to desired levels. Riparian zones, including intermittent flow streams zones, are expanded, to desired levels. MCWPP outreach efforts support strategies that result in riparian areas that support beneficial uses. Lincoln SWCD has a stable funding source to work with agricultural and other landowners. | Water providers |  | PHASE II | 200000 | Business Oregon's One-Stop to develop funding strategy. OHA's Safe Drinking Water Revolving Loan Fund (SDWRLF).
SOURCE WATER DEVELOPMENT AND PROTECTION IMPERATIVE | Effectively use limited water supplies, especially during times of water shortage. Reduce water use. | 45. Seek additional and alternative sources of water in the region. Consider existing studies for additional water sources, such as the 2001 CH2MHill Report on the Rocky Creek Regional Water Supply Project and Preliminary Water Management Plan, and conduct an updated analysis of supply and demand (considering the Multi-jurisdictional Natural Hazard Mitigation Plan and other risks, e.g., cyberscecurity). Using the Water Management Economic Assessment Model (Oregon State University, Oregon Water Resources Department, and MCWPP are developing a Water Management Economic Assessment Model using existing water supply, pricing, and consumption data integrated with climate change projections to simulate the impact of future water shortages and illustrate trade-offs among potential adaptation measures.), develop a suite of adaptation measures (e.g., storage investments, conservation rebate programs, and new pricing models) to address existing and predicted water shortages in the region. | Increase in the amount of water stored (natural) for summer withdrawals. | Updated analysis of supply and demand (use OSU Study) coupled with an alternatives analysis of potential strategies to reduce demand and/or increase supply (conservation, pricing, storage, reuse, etc.) Watershed Management Plans are developed that incorporate water source strategies. Document updated supply and demand projections for individual users and the region as a whole, including an analysis of alternatives and costs/benefits to meet current and future needs. | Lincoln County, DLCD | MCWCC, OWRD | PHASE I | 200000 | OWRD Feasibility Study Grants
|  | 46. Seek and identify opportunities to collect and store water (e.g., expanding raw water impoundments) in the winter season to be used in the summer as a replacement for summer withdrawals. |  | Raw water impoundments hold adequate storage for summer withdrawals. | MCWCC |  | PHASE II | 250000
|  | 47. Advocate for and support multi-benefit water storage opportunities, such as collecting and storing water in the winter season to be used in the summer as a replacement for summer withdrawals and as a source for summertime streamflow augmentation. |  | Options for multi-benefit water storage in the Mid-Coast region are identified and evaluated. Opportunities for small dispersed water storage projects are assessed. | (note:scale determines lead): Water providers, counties, landowners | OWRD | PHASE II | 100000
|  | 48. Evaluate how much natural storage could be produced in the region/subareas as well as limitations to achieving natural storage (e.g., incised stream channels). |  | An assessment of how much natural storage can be produced in the region is conducted, including an articulation of limitations to achieving natural storage. | MidCoast Watersheds Council | USGS, Federal agencies | PHASE I | 150000
|  | 49. Explore resources available to support community source water protection activities. |  | Resources (e.g., carbon credits, carbon exchange, tax credits, and acquisition opportunities) are explored and implemented. | MCWPP |  | PHASES I-II | 50000
|  | 50. Support the reduction of nutrient inputs to source water from all sectors to prevent algal blooms (e.g., Agricultural nutrient management plans, grants, well water nitrate screening, well water and septic system education, low-input gardening). (a) Evaluate specific cases if & when HABs are affecting source water in Planning Area; (b) educate and support the reduction of nutrient inputs to source water from all Sectors to prevent algal blooms (e.g., Ag nutrient management plans, grants, well water nitrate screening, well water and septic system education, low-input gardening). |  | Property owners linked to septic loan program (Craft3). workshops/education events to reach target audience; Homeowners improve practices, reduced nutrient contributions from all Sectors/land uses. | DEQ, OHA (Step a). OHA, OSU Extension, LSWCD, ODA (Step b). |  | PHASES I-III | 150000
|  | 51. Enhance reservoir security. |  | Water reservoirs in the Mid-Coast region are secure. | Water providers, MCWCC |  | PHASE I | 250000 | OWRD Feasibility Study Grants. OHA's Safe Drinking Water Revolving Loan Fund (SDWRLF).
|  | 52. Evaluate specific cases if and when harmful algal blooms are affecting source water. |  | The causes of harmful algal blooms affecting source water are investigated. | Water providers | Land managers | PHASES I-III | 100000
|  | 53. Advocate for integrated pest management (e.g., minimize aerial spraying in watersheds adjacent to source water; promote hand clearing in riparian zones (versus hand spraying); support notification of all water treatment facilities when and where spraying will occur). |  | Agencies and OSU deliver education on safe pesticide application practices; possible formation of a Pesticide Stewardship Partnership; reduction and/or elimination of pesticide use. | ODA, ODF, OSU Extension, DEQ, OHA, OWRD, USFS, County, water providers |  | PHASES I-III | 100000
|  | 54. Furthering a working lands concept, advocate for incentives, and other strategies, that promote silvicultural practices that support restoration of watershed ecological function and protect drinking water source areas. |  | Incentives and other strategies are developed that support watershed ecological function and protection of source drinking water. | MCWPP |  | PHASES I-III | 100000 | Oregon Watershed Enhancement Board Conservation Reserve Enhancement (CREP) TA Program.
ECOSYSTEM PROTECTION AND ENHANCEMENT IMPERATIVE | Restore watershed ecological function (ridgetop to ocean approach), including restoring riparian areas and instream habitat functions, values, and benefits; re-establishing hydrologic and sediment transport regimes to a more natural state; restoring natural channel morphology; protecting, maintaining, and improving water quality in the region for all beneficial uses; and implementing watershed restoration projects that (a) cool streams and improve summertime flows for sensitive species and water quality impairments, and (b) identify, meet, protect, and restore peak and ecological flows. Balance instream and out-of-stream water uses. Ensure summer stream flows are sufficient to meet the instream water needs of fish and wildlife. Consistently attain water quality standards that protect drinking water and other beneficial uses. Anticipate and prepare for the effects of climate change stressors, which are predicted to influence precipitation, temperature, coastal inundation, ecosystem function, and water quality. Prioritize restoration work and support land practices that reduce drinking water contaminants. Identify, meet, protect, and restore peak and ecological flows. Promote natural water storage using beavers and green infrastructure. | 55. Riparian Restoration; Restore Channels; Floodplain Reconnection; Restore Stream Flow: Advocate for a working lands approach (i.e., recognizing the existence of, and working with a diversity of landowners and their goals in the Mid-Coast landscape) and the value and implementation of watershed restoration projects in locations that will achieve the greatest ecological returns on investment (e.g., cool streams and improved summertime flows for sensitive species and water quality impairments). | Ecological function is enhanced throughout Mid-Coast watersheds. Land is preserved in priority areas. Stream habitat projects are implemented to address key limiting factors. Native trees and shrubs are planted on floodplains. Invasive weed treatments are applied. Lateral side-channels are reconnected. Water rights transactions keep more water in streams and incorporate conservation and water efficiency strategies. No net loss in working lands acreage in the Mid-Coast region of Oregon. Net increase in land acquision and easements that protect water quality. | A diversity of landowners participate in the implementation of restoration projects that enhance ecological function in the region. | OWEB, MCWPP, watershed councils | SWCDs, Salmon Safe, Mid-Coast Watersheds Council, ODF, US Forest Service, LCSW, ODFW, volunteers | PHASES I-III | 5000000
|  | 56. Riparian Restoration; Restore Channels; Floodplain Reconnection; Restore Stream Flow: Prioritize streams reaches for buffer establishment using established methods (field assessment, remote sensing, and physical models (e.g., Heat Source)) combined with local knowledge. Advocate for increasing wooded buffer zones associated with intermittent and non-fish bearing streams that feed source water as well as perennial streams that are not currently regulated (e.g., rural residential, urban, legacy agricultural areas). |  | Healthy riparian areas. Achieve a clear understanding of locations/stream reaches where preservation of existing functional buffers would result in greatest protection against degradation of existing water quality. | USFS, private landowners, ODF, DEQ, OWRD, ODFW, Mid-Coast Watersheds Council |  | PHASE II | 250000
|  | 57. Riparian Restoration; Restore Channels: Advocate for the restoration and conservation of native riparian vegetation to facilitate large natural wood recruitment, maintain water quality, ensure ecological function, and produce habitat for beavers. |  | Native riparian vegetation is restored and conserved to enhance ecological function in the region. Woody buffer zones associated with intermittent and non-fish bearing streams are increased. Riparian zones, including intermittent flow stream zones, are expanded and/or restored, to levels that provide adequate ecological functions. | DEQ, OWRD, ODFW, Mid-Coast Watersheds Council, ODA, ODF | All watershed councils, US Forest Service, LCSW | PHASE I | 250000
|  | 58. Riparian Restoration; Restore Channels: Encourage longer forest rotations and implement more erosion control practices. |  | There is less sediment delivery to regional streams. Private forests are managed for multiple benefits, including ecological function and values. Larger proportion of road network is hydrologically disconnected from streams; private forest operations widely implement the Oregon Plan voluntary measures. | USFS, DEQ, LCSW, OWRD, private forestry, ODF, private landowners |  | PHASE II | 250000
|  | 59. Riparian Restoration; Restore Channels; Forest Road Repair: Seek funding opportunities to reduce landslide and other sediment delivery hazards (e.g., undersized culverts, outdated road maintenance, legacy roads) in locations not currently regulated. |  | Mid-Coast region areas that are not currently regulated will experience reduced landslides and contribute fewer sediments to streams. | MCWPP |  | PHASES I-III | 150000
|  | 60. Floodplain Reconnection: Protect beaver populations and encourage beaver pond creation. |  | Stored water for low summer flows is increased. | US Forest Service, Mid-Coast Watersheds Council, ODF |  | PHASE I | 150000 | Bureau of Reclamation Cooperative Watershed Management Grant (Phase I)
|  | 61. Riparian Restoration; Restore Channels; Restore Stream Flow: Implement restoration projects with partners to directly address impairments and improve conditions (e.g., erosion prevention and control, riparian and wetland buffers, urban tree protection). |  | Restoration projects are collaboratively implemented to address limiting factors and improve ecologicl function. | Watershed councils, DEQ, ODFW, LSWCD, water providers, OSU Extension |  | PHASE III | 250000
|  | 62. Restore Stream Flow: Evaluate the mechanisms and conditions for restoring hyporheic flows (the transport of surface water through sediments in flow paths that return to surface water) in the Mid-Coast using a suite of strategies (articulated in the Oregon Plan and other plans). |  | Channel conditions and watershed mechanisms exist for restoring hyporheic flows. Mechanisms, conditions, and locations for restoring hyporheic flows are identified. Projects to restore hyporheic flows are developed and implemented. |  |  |  | 150000
|  | 63. Restore Stream Flow: Recommend that further appropriation of water on high priority streams for meeting aquatic life needs is limited. |  | Further appropriation of water on high priority streams is limited to protect native fish and wildlife. The criteria for high priority streams is identified (e.g., streams where lack of summertime flow is deficient). High priority streams have limited further appropriation of water, addressing the interests and concerns of multiple stakeholders and their interests and values. | OWRD, MidCoast Watersheds Council | Confederated Tribes of Siletz Indians of Oregon | PHASE II | 150000 | Charlotte Martin Foundation Wildlife and Habitat Grant
|  | 64. Restore Stream Flow: Support increased water retention capacity in channels, floodplains, and adjacent uplands and wetlands using a variety of strategies. |  | Strategies are implemented that increase water retention capacity in Mid-Coast channels, floodplains, uplands, and wetlands. | OR DEQ, ODFW, ODF, Mid-Coast Watersheds Council, OWRD |  | PHASES I-III | 10000000 | OWEB Focused Investment Partnership (FIPs), Bureau of Reclamation Cooperative Watershed Management Grant (Phase I)
|  | 65. Restore Stream Flow: Determine ecological flows and establish in-stream needs. Expand the geographic range of flow restoration efforts by identifying flow restoration priorities. |  | Ecological flows are identified for the highest priority waterways. | ODFW, DEQ | OWRD, Mid-Coast Watersheds Council, water users | PHASE I | 250000
|  | 66. Restore Stream Flow: Use established voluntary programs to convert existing water rights (e.g., irrigation, commercial use, other out-of-stream uses) to instream use. Establish, or obtain additional, or transfer existing instream, water rights, where needed, to protect the full suite of flows for fish and wildlife, water quality, recreation, and scenic attraction. |  | An analysis is conducted in Mid-Coast watershed basins to prioritize instream water rights. In-stream water rights are established that protect the full suite of flows for a diversity of uses. | ODFW, DEQ, OWRD, OPRD (state agencies for new rights) | McKenzie River Trust, MidCoast Watersheds Council, OWRD, OWEB (nonprofits for existing rights), water rights holders | PHASE 1 for analysis PHASE 2 to obtain or transfer rights | 250000 | OHA's Safe Drinking Water Revolving Loan Fund (SDWRLF) (Purchase of water rights needed to address an imminent public health threat).
|  | 67. Control Invasive Weeds: Identify priority invasive species in each watershed, and seek funding to support control and management of invasives along stream corridors while encouraging establishment of native vegetation. |  | Priority invasive species are identified, controlled and managed. Prevent new invasive species introductions and decrease the scale and spread of current infestations. | Mid-Coast Watersheds Council, ODA | Oregon Invasive Species Council, local watershed groups, ODF | PHASES I-III | 250000 | Oregon Invasive Species Council (OISC) Invasive Species Education and Outreach Grant
|  | 68. Protect Existing Complex Forest; Strategic Thinning; Prescribed Fire; Promote Native Understory Vegetation: Advocate for implementation of the Lincoln County Multi-Jurisdictional Natural Hazard Mitigation Plan, especially as it relates to wildfire mitigation in the Mid-Coast. |  | Implementation of the Lincoln County Multi-Jurisdictional Natural Hazard Mitigation Plan, especially as it relates to wildfires, is supported throughout the Mid-Coast Region | Lincoln County |  | Phase I | 150000
|  | 69. Easements and acquisitions: Acquire land, or obtain conservation easements, to protect critical land areas managed for water quality protection. |  | Land is purchased (or placed into conservation status) in source water areas/watershed. Key areas are publically owned and managed, or managed for conservation. An increasing proportion of DWSA comprise protected acreage. | Counties, Cities/water districts, Watershed councils, OWEB, NGOs, NRCS, Corporations (Boeing, Microsoft, ext.) |  | PHASES I-II | 10000000